6200COMP Project
Monthly Supervision Meeting Record

Progress Report #3

Month: January 2026

This form should be completed in the first instance by the student based on the progress up to 23 January 2026. The first draft should be sent by email to the supervisor by that date. The student should use the next progress meeting to discuss the points raised in this form with their supervisor. A final signed form should be uploaded to Canvas by 30 January 2026.

Note: Timely adherence to monthly progress reporting schedule is part of the Project Management mark component. Failure to upload agreed and signed monthly report timely will affect your Project Management mark adversely.

Student’s Name: Arwa Daaboul

Supervisor’s Name: Dr Hoshang Kolivand

- Main issues / Points of discussion / Progress made

- Delivered the Jan 16th presentation to my supervisor and moderator. - Google Form questionnaire is ready. - Drafted core sections of Chapter 2 (Literature Review) and started drafting Chapters 3 & 4. - Requirements Engineering and defined the research framework.

- List of actions for the next month

- Chapter 3: Write Requirements Analysis and create the framework diagram. - Chapter 4: Create UML diagrams (Visio) and outline algorithms. - Coding: Set up Python environment and begin model training. - Data Collection: Distribute the survey link to students.

- List of deliverables for next time

- UML diagrams creation - Initial drafts of Chapters 3 & 4. - Initial results from the survey and the machine learning model.

- Other comments

| Signature (student) | Arwa Daaboul | Date | 30/1/2026 |
| --- | --- | --- | --- |
| Signature (supervisor) |  | Date | 6/03/2026 |